## Design FMEA
Design FMEA
FMEA-Typ: |  | Design
System/Subsystem/Element: |  | Cordless Drill – Drive & Safety
Verantwortlicher FMEA-Leiter: |  | Max Mustermann
Datum/Version: |  | 04.05.2026
Änderungsstand: |  | V1.0 Example
Verknüpfung zur nächsten Ebene: |  | DVP&R / System FMEA
Step Number | Item/Component | Function | Potential Failure | Potential Failure Effect | Severity (S) | Potential Causes | Occurrence (O) | Current Controls | Detection (D) | Risk Priority Number (RPN) | Action Priority (AP) | Recommended Actions | Responsibility | Planned End Date | Actions Implemented | Actual End Date | Severity (S) | Occurrence (O) | Detection (D) | Risk Priority Number (RPN) | Action Priority (AP)
1 | Battery pack / cell assembly | Stores and delivers electrical energy safely | Overheating of the battery pack under high load | Loss of performance, shutdown; in extreme cases fire hazard / user injury | 10 | Insufficient heat dissipation; incorrect cell design | 4 | Thermal simulation; temperature sensor in concept; prototype test under continuous load | 5 | 200 | H | Provide an additional NTC sensor per cell group; validate shutdown limit in software; add thermal pad | Electrical Engineering | 2026-06-15 | Yes | 2026-06-12 | 10 | 2 | 3 | 60 | L
2 | Motor control / MOSFET stage | Controls motor speed and torque | MOSFET fails short-circuited | Motor starts uncontrollably or does not stop; possible gearbox damage | 9 | Voltage spikes during switching off; missing protection circuitry | 3 | Circuit review; component derating; preliminary EMC test | 6 | 162 | M | Add transient protection (TVS); optimize gate resistor; perform worst-case test with blocked rotor | Hardware Development | 2026-06-30 | No |  | 9 | 2 | 4 | 72 | L
3 | Housing / ventilation openings | Protects components and enables airflow for cooling | Ventilation openings become clogged with dust | Increased component temperature, reduced service life, premature shutdown | 7 | Opening geometry too fine; use in dusty environments not sufficiently considered | 6 | Design review; IP protection concept; dust chamber test planned | 5 | 210 | H | Increase opening cross-section; adjust labyrinth geometry; include dust chamber test in DVP | Mechanical Development | 2026-07-10 | Partial | 2026-07-08 | 7 | 3 | 3 | 63 | L
4 | Safety lock / switch | Prevents unintended switch-on during transport | Lock does not reliably engage | Unintended switch-on; possible crushing or cutting injury | 10 | Tolerance stack-up too large; spring force too low; wear | 3 | Tolerance analysis; endurance test 10,000 cycles; operating force test | 4 | 120 | L | Increase spring characteristic; reinforce detent contour; add 30,000-cycle test and drop test | Design Engineering | 2026-07-31 | No |  | 10 | 2 | 3 | 60 | L